## BF Mechanical
Sno | Job | UOM | Quantity | Esl Scope | Vendor scope
Mechanical
BLT Overhauling:
1 | Replacement of upper seal valve seat and disc | EA | 1 |  | √
| Supply of seal and disc and fasteners | SET | 1 | √
| Relief valve and equalizing valve replacement | SET | 1 |  | √
| Supply of relief and equalizing valve and necessary accessories | SET | 1 | √
| Replacement of receiving hopper liner | SET | 1 |  | √
| Supply of receiving hopper liner | SET | 1 | √
Cooling staves replacement in 5,6,7 & 8 th row and damaged bid cooling staves and steel bricks:
2 | Design of 112 nos cooling staves for 5,6,7 &8th row and its necsessary accessories |  |  |  | √
| Design approval of 112 nos cooling staves for 5,6,7 &8th row and its necsessary accessories |  |  | √ | √
| Procurement of staves 112 Nos for 5,6,7 and 8th row and its necsessary accessories | SET | 112 |  | √
| Entire refractory lining of the BF shall be removed before commencement of stave dismantling | LOT | 1 |  | √
| Isolation of water line, removal of water hoses, cutting of pedestal and welding, cutting of bolt capes, stave washer, stave compensator, edge preparation of all cut joints, opening stave bolts | SET | 112 |  | √
| Dismantling of staves and taking out of the furnace, Removing from furnace and Shifting damaged staves to designated places | SET | 112 |  | √
| Erection of cooling staves and bolting it to shell, Any adjustment required for proper fitting, Fixing and welding of all necessary accessories of cooling stave | SET | 112 |  | √
| Design of cooling staves in place of bid cooling staves and its necsessary accessories |  |  |  | √
| Design approval of cooling staves in place of bid cooling staves and its necsessary accessories |  |  | √ | √
| Procurement & Supply of bid cooling staves for replacement and necessary accessories | SET | 16 |  | √
| Dismatling (Total installed 28), 11th row & Erection of bid cooling staves and bolting it to shell Any adjustment required for proper fitting, Fixing and welding of all necessary accessories of cooling stave | SET | 16 |  | √
| Filling ferrum cement/ SiC castable in the gaps between staves as per design. | AU | 1 |  | √
| Welding of salvaged C pipes for bid cooling staves, Connecting of all water hoses | SET | 16 |  | √
| Fixing of thermocouple with the cooling staves | LOT | 1 |  | √
| Damaged water cooled steel bricks to be dismantled | SET | 6 |  | √
| Design of water cooled Steel bricks | SET | 6 |  | √
| Design approval of water cooled Steel bricks |  |  | √ | √
| Procurement & Supply of water cooled steel bricks and its necsessary accessories | SET | 6 |  | √
| Erection of steel bricks and bolting it to shell, Fixing and welding of all necessary accessories of stave | SET | 6 |  | √
| Shifting of scrap generated to designated place and any other activity to facilitate the above jobs | LOT | 1 |  | √
Shell plate damaged section to be replaced between 11.48 m to 13.8 m:
3 | Supply of shell plate (30mm, IS 2062 grade-B) in the required shape. | MT | 3 |  | √
| Supply of structural steel required for the job | TON | 3 |  | √
| Cutting of shell joints at 11.480 m and +13.800 m levels should be done with precision to ensure proper fitment of new with existing shell. Also refer drawings for details of edge preparation | LOT | 1 |  | √
| Dismantled shell segments to be taken to cast house side for removal and should be shifted to designated area | LOT | 1 |  | √
| The shell edges at +11.480 m and +13.800 m levels shall be ground smooth for proper joint welding, All shell segments shall be securely fixed in position with existing shell above using temporary fixtures. • After alignment of all segments, vertical welding of joints shall be carried out. Vertical welding shall be stopped 500mm short of bottom edge to facilitate proper fitment. | LOT | 1 |  | √
| Welding of horizontal joint at +11.480 m level shall be carried out. This shall be followed by welding of horizontal joint at +13.800 m level. | LOT | 1 |  | √
Painting of critical structures and Media pipelines in BF3:
4 | Supply and apply of paints in critical structures and media pipelines | LOT | 1 |  | √
| Structure | MT | 5000 |  | √
| Media pipeline | Sq.m | 2000 |  | √
SGP Launder liner replacement:
5 | Removal of old and damaged liners (U shaped, 1 mtr wide & 0.8 mtr side wall) of Slag granulation plant launder | No | 41 |  | √
| Supply of liners and its accessories | No | 41 | √
| Fabrication of dummy plates and fixing at the outlet of the discharge valve and its removal after job completion | LOT | 1 |  | √
| Fixing of new liners with portland cement at base. Alignment and slope to be maintained as per drawing during fixing | No | 41 |  | √
| Procurement of cement | MT | 1.25 |  | √
| Shifting of scrap and removed liners to designated area | LOT | 1 |  | √
Overhauling of drill machine of cast house:
6 | Dismantling of feed feam and its replacement | No | 1 |  | √
| Supply of feed beam approx 3 mtr. for replacement and its accessories | SET | 1 |  | √
| Replacement of drifter and its accessories | SET | 1 |  | √
| Supply of drifter and its accessories | SET | 1 | √
| Base bolt tightening of drill machine | LOT | 1 |  | √
Overhauling of Mudgun Machine of cast house:
7 | Base bolt tightening of Mudgun machine | LOT | 1 |  | √
Overhauling of Skip drive system:
8 | Procurement of Wire mesh for fabricating safety net | LOT | 1 |  | √
| Installation of Steel safety wire mesh below the Skip bridge of BF3 | LOT | 1 |  | √
| Skip bridge bend rail to be replaced | SET | 4 |  | √
| Supply of bend rail and its accessories | SET | 4 | √
Alignment of Tuyere stock assembly with Bustle main cone:
9 | Design, procurement & installation of taper flanges at suitable location for arresting blast leakages | No | 14 |  | √
Lifting tools tackle, Mobile equipments and job oriented machines
10 | Required number of Welding machines, cutting sets, grinding machines, buffing machines, drill machines, hydraulic jacks, hammers, Pug machines, chain pulley blocks, wire rope Slings, De shackles, Hook chuks (max puller), Manual operated reciprocating pumps, Mechanical winches, Hydras, Hywas, Cranes Etc. |  |  |  | √
| All the above said tools to be certified by third party and test certificates to be presented before gate entry. |  |  |  | √
| All Scaffolding materials required to carry out the job. |  |  |  | √
Pre Shutdown Jobs
11 | Fabrication of hanging platform | Ton | 0.4 |  | √
| Erection of winches ( 10 Ton ) | EA | 2 |  | √
| Fabrication of C plate | Ton | 0.5 |  | √
| Hydro pressure testing of all new & left out cooling staves | EA | 134 |  | √
Quality of Consumables
Note: | All consumables, paints etc will be of standard make, the list of which should be approved by ESL. Shell plates should be made from Ultrasonic Testing plates. Ultrasonic testing & radiography will be done for all weld joints on Blast Furnace shell. Power water & other utilities will be provided at one point. Vedanta safety standards to be followed strictly.

## BF Utility
Sno | Area | Job | UOM | Quantity | Esl Scope | Contractor scope
1 | GCP | Replacement of septum inlet butterfly valve DN 1400 | No | 1 |  | √
|  | Supply of septum valve | No | 1 | √
|  | Supply of gasket | Set | 1 | √
|  | Supply of fastners | Set | 1 | √
2 | GCP | Inspection, cleaning & seal replacement of GCP main inlet goggle valve | No | 1 |  | √
|  | Supply of seals | Set | 1 | √
3 | GCP | Inspection, cleaning & seal replacement of GCP all barrel inlet goggle valve | No | 7 |  | √
|  | Supply of seals | Set | 7 | √
4 | GCP | Inspection, cleaning & seal replacement of GCP main outlet goggle valve | No | 7 |  | √
|  | Supply of seals | Set | 7 | √
5 | GCP | GCP silo bucket elevator repairing | Set | 1 |  | √
|  | Cleaning of bucket elevator |  |  | √
|  | Fabrication of bucket | Set | 1 |  | √
|  | Supply of link | Set | 1 |  | √
|  | Supply of steel (MS plate, channel, angle) | Set |  |  | √
|  | Supply of fasteners | Set | 1 |  | √
9 | BF gas line | Seal pot replacement | No | 2 |  | √
|  | Supply of seal pot | No | 2 | √
10 | C H dedusting | Bag replacement (CH dedusting) | No | 1850 |  | √
|  | Supply of bags | No | 1850 | √
|  | Supply of cages | No | 100 | √
12 | BPRT | Suction filter Bag replacement | No | 400 |  | √
|  | Supply of bags | No | 400 | √
13 | BF3 cooling system | Intermediate cooler valves replacement | No | 28 |  | √
|  | Supply of valves, gaskets & fastners. | Set | 28 | √
14 | BF3 cooling system | Tuyere supply & return valve replacement | No | 28 |  | √
|  | Supply of valves, gaskets & fastners. | Set | 28 | √
15 | BF3 cooling system | Big cooler valves replacement | No | 28 |  | √
|  | Supply of valves, gaskets & fastners. | Set | 28 | √
16 | BF3 cooling system | Intermediate cooler hose pipe replacement | No | 28 | √
|  | Supply of hoses, gaskets & fastners. | Set | 28 | √
17 | BF3 cooling system | Tuyere supply & return hose pipe replacement | No | 28 | √
|  | Supply of hoses, gaskets & fastners. | Set | 28 | √
18 | BF3 cooling system | Brace cooler hose pipe replacement | No | 28 | √
|  | Supply of hoses, gaskets & fastners. | Set | 28 | √
19 | BF3 cooling system | Cooling stave valves replacement | No | 168 |  | √
|  | Supply of valves, gaskets & fastners. | Set | 168 | √
20 | BF3 cooling system | Servicing of BF3 industrial water diesel engine & trial in load | Set | 1 |  | √
|  | Supply of spares | Set | 1 | √
|  | Supply of consumables | Set | 1 | √
21 | BF3 cooling system | Cooling Pipeline replacement | Inch Mtr | 1600 |  | √
|  | Supply of cooling pipe |  |  | √
22 | Pump house | Cooling tower structure replacement | MT | 5 |  | √
|  | Supply of structure material | MT | 5 | √
|  | Structure painting | MT | 5 |  | √
|  | Paint | Ltr. | 200 | √

## ElECT.
Sno | Job | UOM | Quantity | Esl Scope | Vendor scope
ELECTRICAL
1.Overhaulling of 7.2MW, 6.6kV sq cage induction motor
| Removing motor from foundation, shifting to loading site and bringing to Work Place | Lot | 1 |  | √
| Coupling removal and complete dismantling of motor ( if required) |  |  |  | √
| Measurement of coupling gap and recording alignment parameters. Measurement of pad insulation if any. Recording discrepancies/damages if any. |  |  |  | √
| Recording IR/PI, resistance and inductance of winding |  |  |  | √
| Thorough cleaning of stator winding, rotor and all part of motors |  |  |  | √
| Though inspection of stator winding, slots, looseness/displacement in wedges, lacing of coils, terminal leads, core condition, space heaters, RTD’s etc. and its repair. Inspection/testing of terminal bushings and if found damaged same will be replaced with identical bushings. Recording of IR/PI, winding resistance and inductance of winding. Recording resistance of RTD’s and space heaters. |  |  |  | √
| Drying of stator and its varnishing. Applying Red Gel Coat on the winding. Recording IR & PI of winding. |  |  |  | √
| Thorough cleaning of cooling tubes, checking leakage( with hydraulic Pressure) if any and its repair. |  |  |  | √
| Cleaning of rotor, bearings, Lubricating arrangement, internal/external fans and their fans etc. Checking rotor core, looseness/damaged rotor bars, rotor joints, bearing seats, fan hubs and the cooling fans and their minor repair if any. |  |  |  | √
| Correction and lapping of rotor shaft journal portions. |  |  |  | √
| Bearing matching and measurement |  |  |  | √
| Heating the rotor and varnishing with core plate varnish, painting of rotor parts i.e. fan, fan hub and associated parts etc. Applying finishing varnish |  |  |  | √
| Assembly of motor with new bearings and by replacing damaged parts. ( If Required) |  |  |  | √
| Painting of motor with one coat of primer and double coats of synthetic enamel paint confirming IS-5 Shade No.631. |  |  |  | √
| Testing of motor as under: a) IR and PI prior and after overhauling. b) Measurement of Inductance and resistance of winding. |  |  |  | √
| All Tools, Testing equipment, arrangement for overhaulling shall be in contractor scope |  |  |  | √
| Electrical line clearance and Isolation Permit |  |  | √
| Disconnection of Power connections. Disconnection of space heaters terminals and indicative instruments. Listing out the same. |  |  | √
| Provide Power supply to tools & Equipments |  |  | √
| De couple of Motor |  |  | √
2 Design, procurement & installation of tuyere water leak detection system
| Design and specification of flowmeters and control system | set | 14 |  | √
| Procurement of material (flowmeters, cables & accesories). |  |  |  | √
| Installation of flowmeters |  |  |  | √
| Modification in pipe line & laying of cables. |  |  |  | √
| Performace test of leak detection system |  |  |  | √
| All Tools, equipment, arrangement, PPE's shall be in contractor scope |  |  |  | √
| Line Clearence , Isolation & safety permits/PTW |  |  | √
| Power supply to tools/equipments |  |  | √
| Termination of I/O in PLC panels |  |  | √
| Scaling & Programming in PLC |  |  | √
3. Design, procurement & installation of Stave water leak detection system
| Design and specification of flowmeters and control system | set | 5 |  | √
| Procurement of material (flowmeters, cables & accesories). |  |  |  | √
| Installation of flowmeters |  |  |  | √
| Modification in pipe line & laying of cables. |  |  |  | √
| Performace test of leak detection system |  |  |  | √
| All Tools, equipment, arrangement, PPE's shall be in contractor scope |  |  |  | √
| Line Clearence , Isolation & safety permits/PTW |  |  | √
| Power supply to tools/equipments |  |  | √
| Termination of I/O in PLC panels |  |  | √
| Scaling & Programming in PLC |  |  | √
4. Installation of thermocouples in Staves
5 | Installation of Thermocouples at staves | set | 56 |  | √
| Procurement of material (thermocouples, Junction boxes, cables & accesories). |  |  |  | √
| Welding of extension piece & flange |  |  |  | √
| Bolting of flanges |  |  |  | √
| Laying of cables |  |  |  | √
| Installation of JB's |  |  |  | √
| Connections of thermocouples |  |  |  | √
| Line Clearence , Isolation & safety permits/PTW |  |  | √
| Power supply to tools/equipments |  |  | √
| Issue materials from store & shifted to site |  |  | √
5. Design, procurement & installation of flow jam switches in PCI line
| Design and specification of flow switches and control system | set | 14 |  | √
| Procurement of material (flow jam switches, Junction boxes, cables & accesories). |  |  |  | √
| Installation of flow switches |  |  |  | √
| Modification in pipe line & laying of cables. |  |  |  | √
| Performace test |  |  |  | √
| All Tools, equipment, arrangement, PPE's shall be in contractor scope |  |  |  | √
| Line Clearence , Isolation & safety permits/PTW |  |  | √
| Power supply to tools/equipments |  |  | √
| Termination of I/O in PLC panels |  |  | √
| Scaling & Programming in PLC |  |  | √

## Operation
Operation
Sl.no. | Job Description | UOM | Quantity | Esl Scope | Vendor scope
1 | Cleaning of Wall Jams attached with staves | Lot | 1 |  | √
2 | Raking/ cleaning out rebound castable after gunning and disposing at place designated by ESL. | Lot | 1 |  | √
3 | Taking out the dismantled jams and refractories out of the furnace and disposing at place designated by ESL. | Lot | 1 |  | √
4 | Anchor (SS) fixing at top cone | Lot | 1 |  | √
5 | Remote shotcreting /Robot gunning of Furnace & top cone | Lot | 1 |  | √
6 | Necessary manpower, equipments, machineries, hoses, spares, tools tackles etc. |  |  |  | √
7 | Supply of refractory material for gunning. | MT | 120 |  | √
8 | Filling ferrum cement/ SiC castable in the gaps between staves. | Lot | 1 |  | √